## Dashboard
AI-ARTIST AGENT - OPENCLAW + LLM API DASHBOARD
Gesamtfortschritt |  | Tasks Gesamt |  | Tasks Erledigt |  | Tasks In Arbeit |  | Tasks Offen |  | Kritische Risiken | Überfällige Tasks
100% |  | 28 |  | 28 |  | 0 |  | 0 |  | 0 | 0
FORTSCHRITT NACH PHASE
Phase | Beschreibung | Tasks | Erledigt | Fortschritt % | Status | Verantwortlich | Start | Ende | Risiko
P0 | Stack Decision & Project Alignment | 2 | 2 | 100% | Erledigt | Projektleiter | KW22 | KW22 | Niedrig
P1 | Foundation & Safety Service | 5 | 5 | 100% | Erledigt | DevOps Lead | KW22 | KW25 | Mittel
P2 | OpenClaw Runtime & Configured LLM API | 5 | 5 | 100% | Erledigt | AI Engineer | KW23 | KW27 | Hoch
P3 | Cache, Source Tracking & Audit | 3 | 3 | 100% | Erledigt | Backend Engineer | KW25 | KW28 | Mittel
P4 | Knowledge, Image Generation & Curation | 4 | 4 | 100% | Erledigt | AI Engineer | KW27 | KW31 | Hoch
P5 | Channels, Publishing & Integrations | 4 | 4 | 100% | Erledigt | Full-Stack Dev | KW29 | KW34 | Hoch
P6 | QA, Observability & Production | 5 | 5 | 100% | Erledigt | QA/DevOps | KW32 | KW38 | Mittel
Status | Anzahl |  | Prioritaet | Anzahl |  | Validierung | Anzahl | CI Gate | Status
Offen | 0 |  | Kritisch | 15 |  | Tests Gesamt | 28 | docs/unit/integration/security | Definiert
In Arbeit | 0 |  | Hoch | 13 |  | Bestanden | 28 | docs/tree/unit | Bestanden
Erledigt | 28 |  | Mittel | 0 |  | Ausstehend | 0 | implementation | Ausstehend
Blockiert | 0 |  | Niedrig | 0 |  | Blockiert | 0 | security | Keine

## Detailplan
AI-ARTIST AGENT - DETAILPLAN OPENCLAW + PROVIDER-NEUTRAL LLM API
OpenClaw control plane, provider-neutral LLM API reasoning, FastAPI/OPA safety service, ComfyUI image generation
ID | Phase | Task | Status | Prioritaet | Verantwortlich | Start (KW) | Ende (KW) | Dauer (Wochen) | Abhaengigkeit | Risiko | Risiko-Beschreibung | Fertigstellung % | KW22 | KW24 | KW28 | KW32 | KW35 | KW38 | Validation Test | Interface Contract | Validation Status | Finished | Completion Evidence
T01 | P0 | Stack-Entscheidung: OpenClaw + provider-neutral LLM API | Erledigt | Kritisch | Projektleiter | 22 | 22 | 1 | - | Niedrig | Grundsatzentscheidung dokumentiert | 10000% | ##### | [5 empty] | Documentation scan confirms OpenClaw is the control plane, provider-neutral LLM API is primary LLM, and deprecated architecture terms are absent. | Docs consistency | Bestanden | 2026-05-31 | Docs/tracker validation passed
T02 | P0 | Projekt-Dokumentation und Tracker auf neue Stack-Entscheidung aktualisieren | Erledigt | Hoch | Projektleiter | 22 | 22 | 1 | T01 | Niedrig | Repo-Dokumente und Tracker synchronisiert | 10000% | ##### | [5 empty] | Manifest includes all new docs, tracker dashboard totals match detail-plan counts, and validation matrix exists. | Docs + tracker | Bestanden | 2026-05-31 | Docs/tracker validation passed
T03 | P1 | Repository-Scaffold: backend, workspaces, policies, tests, docker | Erledigt | Kritisch | DevOps Lead | 22 | 23 | 2 | T01 | Mittel | Scaffold, tests, lint und compose config validiert | 10000% | ##### | [5 empty] | Tree check confirms backend/, workspaces/, policies/, tests/, and docker-compose.yml exist; base pytest/lint commands are wired. | Repo scaffold | Bestanden | 2026-05-31 | pytest/ruff/tree checks passed
T04 | P1 | Docker Compose fuer PostgreSQL, Qdrant, MinIO, Redis, OPA | Erledigt | Kritisch | DevOps Lead | 22 | 24 | 3 | T03 | Mittel | Lokale Services als Entwicklungsbasis | 10000% | ##### | ##### |  |  |  |  | docker compose config succeeds and service health checks pass for PostgreSQL, Qdrant, MinIO, Redis, and OPA. | Docker Compose | Bestanden | 2026-05-31 | docker compose ps reports all services healthy
T05 | P1 | FastAPI Safety Service: health, canonicalize, classify, policy endpoints | Erledigt | Kritisch | AI Engineer | 23 | 24 | 2 | T03,T04 | Mittel | Policy-seitige Rueckversicherung fuer OpenClaw | 10000% |  | ##### |  |  |  |  | API, health-contract, request-metadata, classification-contract, interface-type, request-identity, text-utility, operation-registry, and reason-message tests call /health, /v1/requests/canonicalize, /v1/requests/classify, and /v1/policy/evaluate with expected schemas, centralized health response payload, centralized workspace/agent metadata mapping, stable fingerprints, direct shared request normalization, centralized classifier confidence/reasons, direct centralized token parsing, centralized operation inference, and centralized policy reason text. | FastAPI Safety Service + classification_contracts.py + request_metadata.py + shared helpers | Bestanden | 2026-05-31 | Safety Service endpoint and classification-contract tests passed; final pytest 404 passed, 1 skipped, 1 warning
T06 | P1 | OPA Default-Deny Policies fuer Writes, Cache-Reuse und Tool-Ausfuehrung | Erledigt | Kritisch | AI Engineer | 23 | 25 | 3 | T05 | Hoch | OPA default-deny policy tests validated | 10000% |  | ##### |  |  |  |  | OPA tests prove write, publish, delete, GitHub write, and cache replay are denied by default and allowed only with valid inputs. | OPA policy | Bestanden | 2026-05-31 | OPA default-deny policy tests passed
T07 | P1 | PostgreSQL Migrationen fuer Query/Source/Cache/Audit Tabellen | Erledigt | Kritisch | Backend Engineer | 24 | 25 | 2 | T04 | Mittel | Disposable PostgreSQL migration validation passed | 10000% |  | ##### |  |  |  |  | Migration test applies schema from empty DB, verifies all query/source/cache/audit tables and indexes, then rolls back cleanly. | PostgreSQL migration | Bestanden | 2026-05-31 | PostgreSQL migration rollback test passed
T08 | P2 | OpenClaw Workspace Skeleton: ai-artist-main | Erledigt | Kritisch | AI Engineer | 23 | 24 | 2 | T03 | Mittel | OpenClaw workspace files and memory seeds validated | 10000% |  | ##### |  |  |  |  | Workspace test confirms SOUL.md, IDENTITY.md, USER.md, AGENTS.md, TOOLS.md, MEMORY.md, and memory folders exist. | OpenClaw workspace | Bestanden | 2026-05-31 | OpenClaw workspace tests passed
T09 | P2 | Provider-neutral LLM API Konfiguration und Smoke Test | Erledigt | Kritisch | AI Engineer | 23 | 24 | 2 | T08 | Mittel | Provider-neutral LLM API smoke validation passed | 10000% |  | ##### |  |  |  |  | Smoke, connection-settings, and response-field tests load DeepSeek model env vars, call the OpenAI-compatible LLM API with a redacted request, and record id/model/content through shared dict/SDK response-field and first-choice message parsing. | Provider-neutral LLM API | Bestanden | 2026-05-31 | LLM API smoke tests passed; first-choice message parsing centralized in response_fields.py
T10 | P2 | OpenClaw Tool Hook ruft FastAPI Safety Service vor Tool Calls | Erledigt | Kritisch | AI Engineer | 24 | 26 | 3 | T05,T08 | Hoch | Safety hook validation passed before adapter execution | 10000% |  | ##### |  |  |  |  | Integration, request-identity, and secret-redaction tests attempt a tool call, build prefixed tool-call trace IDs, call shared secret redaction directly for Safety Service metadata, and confirm Safety Service receives the pre-execution request before any adapter runs. | OpenClaw tool hook | Bestanden | 2026-05-31 | OpenClaw safety hook tests passed; policy metadata redaction calls secret_redaction directly
T11 | P2 | SubAgentOutput Schema und Validierung | Erledigt | Hoch | AI Engineer | 24 | 25 | 2 | T08 | Mittel | Strukturierte Ergebnisse fuer Vergleich/Synthese | 10000% |  | ##### |  |  |  |  | Schema, sub-agent output-constructor, and sub-agent status tests accept valid agent outputs, route output construction/model coercion and status vocabulary through shared modules, and reject missing status, malformed artifacts, invalid confidence, and unstructured errors. | SubAgentOutput + subagent_output_contracts.py + subagent_status.py | Bestanden | 2026-05-31 | SubAgentOutput schema and shared constructor tests passed; final pytest 404 passed, 1 skipped, 1 warning
T12 | P2 | Mock sub-agent orchestration | Erledigt | Hoch | AI Engineer | 25 | 27 | 3 | T11 | Mittel | Deterministic local mock orchestration validated | 10000% | [6 empty] | Orchestration, sub-agent output-constructor, mock-agent-contract, sub-agent status, review-status, and numeric-utility tests route one request through all mock agents, collect structured outputs through the shared constructor, and synthesize status/confidence through shared agent/artifact vocabulary, output/error/synthesis/telemetry contracts, status aggregation, and rounded-average helpers. | Mock sub-agents + subagent_output_contracts.py + shared helpers + mock_agent_contracts.py | Bestanden | 2026-05-31 | Mock sub-agent contract tests passed; output construction centralized in subagent_output_contracts.py; final pytest 404 passed, 1 skipped, 1 warning
T13 | P3 | Approved Read-Only Response Cache | Erledigt | Hoch | Backend Engineer | 25 | 27 | 3 | T06,T07 | Mittel | Nur OPA-freigegebene Read-Antworten | 10000% | [6 empty] | Cache and time-normalization tests verify only read responses with OPA approval and non-expired UTC-normalized cache entries are replayed. | Response cache + time normalization | Bestanden | 2026-05-31 | Cache replay and time utility tests passed
T14 | P3 | Source Freshness Check mit source_data_registry.change_seq | Erledigt | Kritisch | Backend Engineer | 26 | 28 | 3 | T07,T13 | Hoch | Verhindert stale cache replay | 10000% |  |  | ##### |  |  |  | Freshness, source-registry-contract, optional source-registry lookup, and time-utility tests increment source_data_registry.change_seq, verify UTC source timestamps, prove stale cached responses are blocked, and guard shared missing-row message formatting plus optional source-row lookup. | Source freshness + source_registry_contracts.py + find_source | Bestanden | 2026-05-31 | Source freshness tests passed; optional source lookup centralized in find_source
T15 | P3 | Audit Event Log fuer Requests, Reuse und Execution Envelopes | Erledigt | Hoch | Backend Engineer | 26 | 28 | 3 | T07 | Mittel | Nachvollziehbarkeit fuer alle Aktionen | 10000% |  |  | ##### |  |  |  | Audit, observability, secret-redaction, and payload-field tests verify audit events, correlation IDs, shared payload extraction, and telemetry-safe mappings through audit redaction. | Audit log | Bestanden | 2026-05-31 | Audit tests passed; redacted audit mapping helper shared with observability
T16 | P4 | Knowledge Agent + LlamaIndex/Qdrant Retrieval | Erledigt | Hoch | AI Engineer | 27 | 30 | 4 | T12,T14 | Mittel | Kunstwissen, Stilbibliothek, Quellenindex | 10000% |  |  | ##### |  |  |  | Retrieval, knowledge-contract, sub-agent output-constructor, text-utility, contextual-snippet, and numeric-utility tests ingest sample source data, tokenize/embed it through shared helpers, query Qdrant with shared vector similarity, return source-cited results through centralized Knowledge Agent output/snippet contracts, and exclude unapproved sources. | Knowledge Agent + knowledge_contracts.py + subagent_output_contracts.py + text_utils.py | Bestanden | 2026-05-31 | Knowledge Agent retrieval tests passed; output construction centralized in subagent_output_contracts.py; contextual snippets centralized in text_utils.py
T17 | P4 | ComfyUI Adapter hinter Execution Policy Gate | Erledigt | Kritisch | AI Engineer | 27 | 30 | 4 | T06,T10,T12 | Hoch | Bildgenerierung darf Policy nicht umgehen | 10000% |  |  | ##### |  |  |  | Shared model-coercion, direct operation, execution-gate, execution-gate-message, ComfyUI-contract, and time-utility tests plus adapter tests prove image generation is gated, uses centralized gate failure and required-envelope messages plus direct shared UTC expiry checks, and follows centralized generated-image URI conventions. | ComfyUI adapter + model coercion + execution gate + execution_gate_messages.py | Bestanden | 2026-05-31 | T17 tests passed; gated adapter operation constants are called directly; final pytest 404 passed, 1 skipped, 1 warning
T18 | P4 | Image Provenance: Prompt, Modell, Workflow, Seed, Quellen, Review; review status vocabulary/checks use review_status.py | Erledigt | Hoch | AI Engineer | 28 | 31 | 4 | T17 | Mittel | Reproduzierbarkeit und Compliance | 10000% |  |  | ##### |  |  |  | Artifact, review-status, direct model-coercion, direct canonical-hash, payload-field, response-field, ComfyUI-contract, and time-utility tests verify image provenance and storage URI construction. | Image provenance + model coercion + canonical hashing + comfyui_contracts.py | Bestanden | 2026-05-31 | Image provenance tests passed; input coercion calls model_coercion.coerce_model directly
T19 | P4 | Critic/Curator Rubrics fuer Bildqualitaet und Stilpassung | Erledigt | Hoch | Domain Expert | 28 | 31 | 4 | T12,T17 | Mittel | Qualitaetssteuerung des kreativen Outputs | 10000% |  |  | ##### |  |  |  | Critic-rubric, review-status, text-utility, numeric-utility, direct numeric-clamp, and direct model-coercion tests score sample images or mocked image metadata with shared rubric vocabulary and direct shared scoring helpers. | Critic rubric vocabulary + direct numeric clamps + model coercion | Bestanden | 2026-05-31 | Critic/Curator tests passed; score clamping calls numeric_utils.rounded_clamp directly
T20 | P5 | Slack Development Channel Integration | Erledigt | Hoch | Full-Stack Dev | 29 | 31 | 3 | T10,T12 | Mittel | Bedienkanal fuer Team-Tests | 10000% | [6 empty] | Slack adapter, Slack-contract, connection-settings, request-identity, payload-field, and secret-redaction tests use a mocked Slack API to confirm inbound request normalization, nested event object validation, centralized Slack source labels, adapter validation messages, and runtime bot-token resolution, stable request IDs, direct shared helper usage at the adapter boundary, outbound response formatting, and token redaction. | Slack adapter + request identity + payload fields + slack_contracts.py | Bestanden | 2026-05-31 | Slack adapter, request identity, and payload field tests passed
T21 | P5 | Source Ingestion fuer Kunst-/Mode-/Trendquellen | Erledigt | Hoch | Full-Stack Dev | 30 | 33 | 4 | T16 | Hoch | ToS und Quellenqualitaet pruefen | 10000% |  |  |  | ##### |  |  | Ingestion, source-ingestion-contract, canonical-hash, URL utility, and source-registry lookup tests import approved sample sources, store snapshots, record source registry rows, call shared approved-domain/rejection contracts, hash/version, URL-domain, and optional registry lookup helpers directly, create stable source version tags, and reject disallowed or non-http source domains. | Source ingestion + source_ingestion_contracts.py + canonical version tags + URL validation + find_source | Bestanden | 2026-05-31 | Source ingestion contract tests passed; approved domains and rejection text centralized in source_ingestion_contracts.py; final pytest 404 passed, 1 skipped, 1 warning
T22 | P5 | Publishing Agent mit Human Approval fuer externe Writes; publishing statuses use publishing_status.py | Erledigt | Kritisch | Full-Stack Dev | 31 | 34 | 4 | T06,T15,T20 | Hoch | Publizieren bleibt gated | 10000% |  |  |  | ##### |  |  | Shared direct operation, execution-gate, execution-gate-message, canonical ID, response-field, publishing-status, side-effect audit, and publishing tests prove external publishing remains blocked until human approval is attached and audit operation/status plus required-envelope errors are read through shared operation/response/status/message boundaries. | Publishing approval + operations + execution gate; publishing statuses use publishing_status.py + execution_gate_messages.py | Bestanden | 2026-05-31 | T22 tests passed; gated adapter operation constants are called directly; final pytest 404 passed, 1 skipped, 1 warning
T23 | P5 | GitHub Adapter hinter Execution Envelope | Erledigt | Hoch | Full-Stack Dev | 31 | 33 | 3 | T15,T22 | Mittel | Token bleibt ausserhalb der Agent-Kontexte | 10000% |  |  |  | ##### |  |  | GitHub adapter, GitHub-contract, connection-settings, execution-gate-message, direct operation registry, URL utility, HTTP-method, and adapter-result tests use a mocked GitHub API, resolve git_ai-artist_codex_token through the shared runtime secret resolver, call shared operation and URL path validation directly, reject unsafe API paths and non-write methods before token reads, centralize required-envelope and GitHub adapter validation errors, and confirm the token is read only by the adapter, not agents. | GitHub adapter + operations + URL validation + execution_gate_messages.py + github_contracts.py | Bestanden | 2026-05-31 | T23 tests passed; gated adapter operation constants are called directly; final pytest 404 passed, 1 skipped, 1 warning
T24 | P6 | Unit Tests fuer Safety Service und Policies | Erledigt | Kritisch | QA Engineer | 32 | 34 | 3 | T05,T06,T07 | Mittel | Regressionen in Sicherheitslogik verhindern | 10000% |  |  |  | ##### |  |  | CI test suite runs canonicalizer, health-contract, request-metadata, classification-contract, sub-agent output-constructor, direct runtime interface-type imports, registry-driven connection settings/runtime env/runtime secret/env-access guard/endpoint URL composition/env-example rendering and shell-command construction/process execution/delimited output parsing and readiness backup path contracts and repo-root/workspace/repo artifact path/source-read/backend-module-discovery/raw-open-source-inspection contracts, canonical hashing/version tags/HMAC signatures/security-review/test-serialization/text-hash/image-provenance-hash contracts, source-ingestion approved-domain/rejection contracts, direct source-ingestion hash/version and URL-domain boundaries, source-registry missing-row message contracts and optional lookup, execution-gate failure and required-envelope message contracts, direct request identity/trace IDs, runtime IDs, mapping utilities, cache request-kind/operation constants, cache/policy/execution reason messages, sub-agent statuses, mock-agent contracts including orchestration output/error/synthesis/telemetry text, Knowledge Agent contracts and contextual snippets, ComfyUI contracts including response validation messages, review statuses, critic rubric vocabulary, Slack and GitHub contract and boundary helper usage, shared secret detection/redaction and file-scanning boundaries, direct gated-adapter operation constants, publishing operation/status boundaries, observability constants and redacted audit mappings, direct text utilities, Markdown heading utilities, direct numeric utility use at rubric boundaries, time utilities with direct-wrapper and test current-time guards, payload fields/nested objects, response fields including first-choice message parsing, URL utilities with direct connector-boundary usage, HTTP method normalization, operation registry, direct model coercion at adapter/domain boundaries, classifier, OPA, cache, freshness, and audit unit tests with --cov-fail-under=90 over the safety service modules. | Safety Service + classification_contracts.py + source_ingestion_contracts.py + connection endpoint/env-example rendering + shell_commands.py + readiness_paths.py + repo_paths.py + shared helpers | Bestanden | 2026-05-31 | Unit CI coverage gate passed; readiness backup and repo-root/workspace/repo artifact path/source-read/backend-module-discovery/raw-open-source-inspection contracts included in coverage; final pytest 404 passed, 1 skipped, 1 warning
T25 | P6 | Integration Tests fuer OpenClaw -> Safety Service -> Mock Agents | Erledigt | Kritisch | QA Engineer | 33 | 35 | 3 | T10,T12,T24 | Hoch | End-to-End Verhalten absichern | 10000% |  |  |  |  | ##### |  | End-to-end test sends request through OpenClaw hook, Safety Service, mock agents, validation, and final synthesis.; status aggregation uses subagent_status.py | Integration CI | Bestanden | 2026-05-31 | OpenClaw-to-safety integration tests passed
T26 | P6 | Observability: OpenTelemetry, Prometheus, Loki, Grafana; telemetry stages/log levels use observability.py | Erledigt | Hoch | DevOps Lead | 34 | 36 | 3 | T15,T25 | Mittel | Betriebssichtbarkeit | 10000% |  |  |  |  | ##### |  | Telemetry, request-metadata, audit-redaction, and observability-constant tests verify trace ids, metrics, structured logs, stage constants, log-level constants, shared workspace/agent metadata mappings, and shared redacted mapping helpers are used for request, policy, cache, orchestration, and tool stages. | Observability + request_metadata.py + audit redaction | Bestanden | 2026-05-31 | Observability tests passed; request metadata mapping centralized for request fingerprints and observability fields
T27 | P6 | Security Review: Secrets, Configured LLM API Payloads, Scraping, Publishing; publishing statuses use publishing_status.py | Erledigt | Kritisch | Projektleiter | 35 | 36 | 2 | T21,T22,T23 | Hoch | Compliance und Token-Grenzen | 10000% |  |  |  |  | ##### |  | Shared detection/redaction/file-scanning tests and security checklist tests scan logs, prompts, memory, audit payloads, artifacts, and canonical JSON serialization paths for secret patterns, assignment-style leaks, and policy bypasses. | Security review | Bestanden | 2026-05-31 | Security review tests passed; reviewable text-file discovery centralized in file_scanning.iter_review_text_files
T28 | P6 | Production Hardening und Runbooks | Erledigt | Hoch | DevOps Lead | 36 | 38 | 3 | T25,T26,T27 | Mittel | Uebergang von MVP zu Betrieb | 10000% | [5 empty] | ##### | Readiness, connection-settings, shell-command, readiness-path, repo-path, health-contract, and Markdown utility tests confirm runbooks, backups, restore check, env validation, centralized .env.example rendering, centralized service URL composition, shell command construction/process execution/delimited output parsing, backup directories, container dump path, MinIO source alias, Compose/env/runbook/OPA/PostgreSQL schema paths, centralized health-check expected signals, retention policy, incident contacts, and shared Markdown heading parsing exist. | Production readiness + shell_commands.py + readiness_paths.py + repo_paths.py + connection env/example and endpoint URLs + health_contracts.py + markdown_utils.py | Bestanden | 2026-05-31 | Production readiness and repo path tests passed; repo artifact paths, repo-root lookup, workspace file lookups, backend module discovery, and backend module source reads flow through repo_paths.py; final pytest 404 passed, 1 skipped, 1 warning
Gesamtfortschritt:

## Offene Fragen
OFFENE FRAGEN - AI-ARTIST OPENCLAW + LLM API
# | Kategorie | Frage | Auswirkung | Priorität | Verantwortlich | Status
1 | Infrastruktur | Lokaler GPU-Server oder Cloud GPU fuer ComfyUI? | Kosten, Latenz, Skalierung | Hoch | DevOps Lead | Offen - MVP bevorzugt Cloud oder vorhandene lokale GPU
2 | LLM Provider | Welcher LLM-Provider als Backend? | Kosten, Qualitaet, Datenschutz | Kritisch | AI Engineer | Erledigt - provider-neutral LLM API als Primary
3 | Image Gen | Primaeres Modell: Flux, SDXL, oder mehrere parallel? | GPU-Anforderungen, Qualitaet | Hoch | AI Engineer | Offen - ComfyUI Adapter vorbereitet mehrere Workflows
4 | Image Gen | Fine-Tuning eigener Modelle geplant? | Einzigartigkeit, Aufwand | Mittel | AI Engineer | Spaeter - nicht MVP
5 | Social Media | Instagram API: Business Account vorhanden? | Trend-Monitoring Funktionalitaet | Hoch | Full-Stack Dev | Offen - nach Safety/Audit
6 | Social Media | X/Twitter API Tier und Budget? | Kosten und Verfuegbarkeit | Mittel | Projektleiter | Offen - nach MVP
7 | Legal | Copyright-Strategie und AI-Content Kennzeichnung? | Compliance-Risiko | Kritisch | Projektleiter | Offen - vor Publishing Agent
8 | Budget | Monatliches Budget fuer LLM API, GPU und Social APIs? | Betriebskosten | Kritisch | Projektleiter | Offen
9 | Architektur | OpenClaw Version und Pinning-Strategie? | Stabilitaet vs. Features | Hoch | DevOps Lead | In Arbeit - latest stable pinnen
10 | Slack | Slack-Channels getrennt pro Agent oder gemeinsamer Dev Channel? | Kommunikationsstruktur | Mittel | Alle | Offen - Dev Channel zuerst
11 | Budget | Monatliches Budget für API-Calls (LLM + Social Media)? | Betriebskosten | Kritisch | Projektleiter | Offen
12 | Budget | GPU-Kosten: Wie viele Bilder/Tag geplant? | Infrastruktur-Dimensionierung | Hoch | DevOps Lead | Offen
13 | Team | Teamgröße und verfügbare Rollen? | Timeline, Parallelisierung | Hoch | Projektleiter | Offen
14 | Team | Domain-Expertise Kunst/Mode intern vorhanden? | Wissensaufbau-Aufwand | Mittel | Projektleiter | Offen
15 | Architektur | OpenClaw Gateway: Single-Instance oder Cluster? | Skalierbarkeit, Kosten | Mittel | DevOps Lead | Offen
16 | Architektur | Wie viele Sub-Agents initial? Erweiterbar? | Komplexität, Kosten | Hoch | AI Engineer | Offen
17 | Content | Welche Kunststile/Genres als Fokus? (Abstrakt, Fotorealistisch, etc.) | SOUL.md Design, Modellwahl | Hoch | Domain Expert | Offen
18 | Content | Output-Format: Nur Bilder oder auch Video/Animation? | GPU-Anforderungen, Toolchain | Mittel | AI Engineer | Offen
19 | Content | Zielgruppe: Kunstsammler, Social-Media, Print, NFT? | Go-to-Market, Output-Qualität | Hoch | Projektleiter | Offen
20 | Datenschutz | Wo werden generierte Bilder gespeichert? (S3, lokal, IPFS?) | Kosten, Verfügbarkeit | Mittel | DevOps Lead | Offen
21 | Qualität | Automatische vs. manuelle Qualitätskontrolle der Bilder? | Workflow, Human-in-the-Loop | Hoch | AI Engineer | Offen
22 | Monitoring | Welche Metriken definieren 'Erfolg' des Agenten? | KPI-Definition | Hoch | Projektleiter | Offen
23 | Integration | Bestehende Systeme die integriert werden müssen? | Scope, Timeline | Mittel | Full-Stack Dev | Offen
24 | OpenClaw | OpenClaw Version: Stable oder Latest? Update-Strategie? | Stabilität vs. Features | Mittel | DevOps Lead | Offen
25 | Slack | Slack-Channels: Getrennte Channels pro Agent oder gemeinsam? | Kommunikationsstruktur | Mittel | Alle | Offen

## Architektur
SYSTEMARCHITEKTUR - AI-ARTIST OPENCLAW + LLM API
Komponente | Typ | Technologie | Beschreibung | Abhängig von | Port/Endpoint | Status | Verantwortlich
OpenClaw Gateway | Core | OpenClaw latest stable | Agent control plane, workspace loader, channel adapters | - | OPENCLAW_GATEWAY_URL | Ausgewaehlt | DevOps Lead
AI-Artist Main Agent | Agent | OpenClaw + SOUL.md | Kreativdirektor, Planung, Kuratierung, Delegation | Gateway | via OpenClaw | Geplant | AI Engineer
Configured LLM API | Extern | Provider-neutral LLM API | Primaeres Reasoning, Kritik, Planung, Multimodalitaet | deepseek-open-art standard key | HTTPS | Ausgewaehlt | AI Engineer
FastAPI Safety Service | Backend | FastAPI + Python 3.11 | Canonicalizer, classifier, OPA client, audit, cache, execution envelope | OpenClaw | localhost:8000 | Naechster Schritt | AI Engineer
OPA Policy Layer | Policy | OPA/Rego | Default-deny fuer Writes, Reuse und privileged execution | Safety Service | localhost:8181 | Geplant | AI Engineer
PostgreSQL | Data | PostgreSQL | Request runs, source registry, cache, audit metadata | Docker Compose | localhost:5432 | Geplant | Backend Engineer
Qdrant | Data | Qdrant | Vector retrieval fuer Knowledge Agent | Docker Compose | localhost:6333 | Geplant | Backend Engineer
MinIO | Storage | MinIO | Generated images, source snapshots, response artifacts | Docker Compose | localhost:9000 | Geplant | DevOps Lead
ComfyUI Server | Backend | ComfyUI + Flux/SDXL | Bildgenerierung hinter Execution Policy Gate | GPU worker | localhost:8188 | Geplant | AI Engineer
Slack Integration | Channel | OpenClaw Slack Adapter | Dev channel first, publishing later | Gateway, Slack API | Webhook/API | Geplant | Full-Stack Dev
Observability | Infra | OpenTelemetry + Prometheus + Loki + Grafana | Traces, metrics, logs, dashboards | Alle Komponenten | Grafana | Geplant | DevOps Lead
AGENT-KOMMUNIKATIONSFLUSS
Von | Nach | Kanal | Nachrichtentyp | Beispiel | Frequenz
Social Scout | Main Agent | Inter-Agent / Slack | Trend-Report | "Neon-Surrealismus trendet auf Pinterest +340%" | 4x täglich
Main Agent | Image-Gen Agent | Inter-Agent / Slack | Bildauftrag | "Erstelle: Neon-surreales Stadtbild, Flux 2, 1024x1024" | Nach Trend-Analyse
Image-Gen Agent | Main Agent | Inter-Agent / Slack | Bild-Ergebnis | "4 Varianten generiert, CLIP-Score: 0.87" | Pro Auftrag
Main Agent | Image-Gen Agent | Inter-Agent / Slack | Feedback | "Variante 2 verfeinern, mehr Kontrast" | Bei Bedarf
Main Agent | Slack Channel | Slack API | Galerie-Post | "Neue Serie: Urban Dreams — 8 Werke" | 1-2x täglich
Social Scout | Slack Channel | Slack API | Trend-Briefing | "Wöchentliches Trend-Briefing KW25" | Wöchentlich

## Requirements
PREREQUISITES, REQUIREMENTS & SKILLS - OPENCLAW + LLM API
Kategorie | Requirement | Details | Kritikalitaet | Beschaffung | Status
Software | OpenClaw latest stable | Agent control plane, workspace files, channel adapters | Kritisch | OpenClaw docs / package source | Ausgewaehlt
Configured LLM API | LLM API access | deepseek-open-art standard key, LLM_API_URL, provider primary lane | Kritisch | LLM API provider | Ausgewaehlt
Software | Python 3.11+ | FastAPI safety service, workers, tests | Hoch | python.org | Ausstehend
Software | Node.js 20+ | OpenClaw runtime | Hoch | nodejs.org | Ausstehend
Software | Docker & Docker Compose | PostgreSQL, Qdrant, MinIO, Redis, OPA | Hoch | docker.com | Ausstehend
Software | ComfyUI | Image workflow engine behind policy gate | Kritisch | ComfyUI project | Ausstehend
AI Modelle | Flux / SDXL | Primary image workflows in ComfyUI | Hoch | Model providers | Ausstehend
Hardware | GPU for ComfyUI | Local 16GB+ VRAM or GPU cloud | Hoch | Kauf oder Cloud | Offen
API Keys | Slack Bot Token | Dev channel integration | Mittel | api.slack.com | Ausstehend
API Keys | GitHub token | git_ai-artist_codex_token only in environment | Hoch | GitHub | Vorhanden/zu pruefen
Team Skills | OpenClaw workspace design | SOUL.md, AGENTS.md, TOOLS.md, MEMORY.md | Kritisch | Docs + Praxis | Aufbauen
Team Skills | Policy and audit design | OPA/Rego, execution envelopes, cache reuse rules | Kritisch | Praxis | Aufbauen
Team Skills | ComfyUI workflow design | Flux/SDXL workflows, provenance | Hoch | Praxis | Aufbauen
Hardware | Storage: min. 500GB SSD | Modelle ~50GB+, Bilder, Logs | Hoch | — | Ausstehend
API Keys | LLM Provider API Key | Any LLM API provider / local model | Kritisch | Provider Website | Ausstehend
API Keys | Slack Bot Token | Bot + App erstellen, Scopes setzen | Hoch | api.slack.com | Ausstehend
API Keys | Instagram Graph API | Business Account erforderlich | Hoch | developers.facebook.com | Ausstehend
API Keys | Pinterest API | Developer Account | Mittel | developers.pinterest.com | Ausstehend
API Keys | X/Twitter API | Basic/Pro Tier (kostenpflichtig) | Mittel | developer.x.com | Ausstehend
Team Skills | OpenClaw Administration | SOUL.md, AGENTS.md, Gateway Config | Kritisch | Docs + Community | Aufbauen
Team Skills | Prompt Engineering (Bild) | Flux/SDXL Prompt-Syntax, Negative Prompts | Kritisch | Training / Praxis | Aufbauen
Team Skills | ComfyUI Workflow Design | Node-Workflows, Custom Nodes | Hoch | Tutorials / Praxis | Aufbauen
Team Skills | Kunsthistorik & Stilkunde | Epochen, Bewegungen, Techniken | Hoch | Literatur / Kurse | Aufbauen
Team Skills | Fotografie & Komposition | Goldener Schnitt, Licht, Farbe | Hoch | Literatur / Praxis | Aufbauen
Team Skills | Python / MCP Development | Custom Skills & MCP Server | Hoch | Docs / Praxis | Aufbauen
Team Skills | Social Media APIs | REST APIs, OAuth, Rate Limiting | Mittel | API Docs | Aufbauen
Team Skills | DevOps / Docker / CI-CD | Deployment, Monitoring | Mittel | Praxis | Aufbauen

## Risiken
RISIKO-REGISTER - OPENCLAW + LLM API
# | Risiko | Wahrscheinlichkeit | Impact | Score | Mitigation | Owner | Status
1 | OpenClaw Integration unklar oder API aendert sich | Mittel | Hoch | 6 | Version pinnen, Adapter duenn halten, Smoke Tests | DevOps Lead | Aktiv
2 | Configured LLM API Kosten steigen | Mittel | Hoch | 6 | Modell-Lanes, Cache, Token Budgets, provider fallback/classifier models fuer Nebenpfade | AI Engineer | Aktiv
3 | Secrets gelangen in Agent-Kontext | Niedrig | Kritisch | 6 | Env-only, Tool Adapter, Audit Redaction, Tests | AI Engineer | Aktiv
4 | Policy Gate wird von Tools umgangen | Mittel | Kritisch | 8 | OpenClaw Tool Hook zentralisieren, Default-Deny OPA | AI Engineer | Aktiv
5 | ComfyUI GPU-Kosten oder Kapazitaet | Hoch | Hoch | 9 | Cloud GPU testen, lokale GPU spaeter, Job Limits | DevOps Lead | Aktiv
6 | Bildqualitaet unter Erwartung | Mittel | Hoch | 6 | Critic/Curator Rubrics, Prompt Iteration, mehrere Workflows | AI Engineer | Aktiv
7 | Copyright oder AI-Content Kennzeichnung | Mittel | Kritisch | 8 | Human Approval, Provenance, Legal Review vor Publishing | Projektleiter | Aktiv
8 | Social API Rate Limits | Hoch | Mittel | 6 | Spaeter integrieren, Caching, Fallback-Quellen | Full-Stack Dev | Beobachten
9 | Cache replay liefert stale Antwort | Mittel | Hoch | 6 | change_seq Freshness, OPA Recheck, Tests | Backend Engineer | Aktiv
10 | Zu grosser MVP Scope | Hoch | Mittel | 6 | Erster Slice: OpenClaw workspace + configured LLM API + safety service + mock agents | Projektleiter | Aktiv
11 | Scraping ToS/Compliance | Mittel | Hoch | 6 | Quellenreview vor Ingestion, erlaubte APIs bevorzugen | Projektleiter | Aktiv
12 | Observability kommt zu spaet | Mittel | Mittel | 4 | Audit zuerst, OpenTelemetry/Grafana ab Integration | DevOps Lead | Beobachten

## Entscheidungen
ENTSCHEIDUNGEN - AI-ARTIST OPENCLAW + LLM API
Datum | Entscheidung | Auswahl | Begruendung | Auswirkung | Status | Owner | Naechster Schritt
2026-05-30 | Agent Control Plane | OpenClaw | Passt zu vorhandener Tracker-Planung mit SOUL.md/AGENTS.md und Channel-Adaptern | FastAPI wird Safety Service statt konkurrierender Gateway | Final | Projektleiter | OpenClaw Workspace scaffolden
2026-05-30 | Primaerer LLM Backend | Provider-neutral LLM API | Schneller MVP, hohe Qualitaet, kein lokaler LLM GPU-Bedarf | Lokale LLMs werden spaeterer Fallback | Final | AI Engineer | deepseek-open-art und Modell-Lanes konfigurieren
2026-05-30 | Image Generation | ComfyUI hinter Execution Policy Gate | Bestehende Projektplanung bleibt nutzbar, Bildjobs bleiben policy-gated | GPU lokal oder Cloud optional | Final | AI Engineer | ComfyUI Adapter mocken
2026-05-30 | Safety Architecture | FastAPI + OPA + PostgreSQL | Audit, Cache-Reuse und privilegierte Aktionen brauchen deterministische Policy | OpenClaw Tools muessen Safety Hook nutzen | Final | AI Engineer | Safety Service MVP bauen
2026-05-30 | MVP Scope | Narrow vertical slice | Erst OpenClaw workspace, configured LLM API smoke test, safety service, mock agents | Social APIs und Publishing spaeter | Final | Projektleiter | Repo scaffold starten

## Validation
VALIDATION MATRIX - AI-ARTIST OPENCLAW + LLM API
ID | Validation Test | Interface Contract | Gate | Status | Finished | Evidence | Owner
T01 | Documentation scan confirms OpenClaw is the control plane, provider-neutral LLM API is primary LLM, and deprecated architecture terms are absent. | Docs consistency | docs-consistency | Bestanden | 2026-05-31 | Docs/tracker validation passed | Projektleiter
T02 | Manifest includes all new docs, tracker dashboard totals match detail-plan counts, and validation matrix exists. | Docs + tracker | docs-consistency | Bestanden | 2026-05-31 | Docs/tracker validation passed | Projektleiter
T03 | Tree check confirms backend/, workspaces/, policies/, tests/, and docker-compose.yml exist; base pytest/lint commands are wired. | Repo scaffold | unit | Bestanden | 2026-05-31 | pytest/ruff/tree checks passed | DevOps Lead
T04 | docker compose config succeeds and service health checks pass for PostgreSQL, Qdrant, MinIO, Redis, and OPA. | Docker Compose | unit | Bestanden | 2026-05-31 | docker compose ps reports all services healthy | DevOps Lead
T05 | API, health-contract, request-metadata, classification-contract, interface-type, request-identity, text-utility, operation-registry, and reason-message tests call /health, /v1/requests/canonicalize, /v1/requests/classify, and /v1/policy/evaluate with expected schemas, centralized health response payload, centralized workspace/agent metadata mapping, stable fingerprints, direct shared request normalization, centralized classifier confidence/reasons, direct centralized token parsing, centralized operation inference, and centralized policy reason text. | FastAPI Safety Service + classification_contracts.py + request_metadata.py + shared helpers | unit | Bestanden | 2026-05-31 | Safety Service endpoint and classification-contract tests passed; final pytest 404 passed, 1 skipped, 1 warning | AI Engineer
T06 | OPA tests prove write, publish, delete, GitHub write, and cache replay are denied by default and allowed only with valid inputs. | OPA policy | security | Bestanden | 2026-05-31 | OPA default-deny policy tests passed | AI Engineer
T07 | Migration test applies schema from empty DB, verifies all query/source/cache/audit tables and indexes, then rolls back cleanly. | PostgreSQL migration | unit | Bestanden | 2026-05-31 | PostgreSQL migration rollback test passed | Backend Engineer
T08 | Workspace test confirms SOUL.md, IDENTITY.md, USER.md, AGENTS.md, TOOLS.md, MEMORY.md, and memory folders exist. | OpenClaw workspace | integration | Bestanden | 2026-05-31 | OpenClaw workspace tests passed | AI Engineer
T09 | Smoke, connection-settings, and response-field tests load DeepSeek model env vars through the shared connection registry/runtime env resolution, runtime secret resolution, and guarded env access, call the OpenAI-compatible LLM API with a redacted request, and record response id/model/content through shared dict/SDK response-field and first-choice message parsing. | Provider-neutral LLM API + connection settings + response fields | unit | Bestanden | 2026-05-31 | LLM API smoke tests passed; first-choice message parsing centralized in response_fields.py | AI Engineer
T10 | Integration, request-identity, and secret-redaction tests attempt a tool call, build prefixed tool-call trace IDs, call shared secret redaction directly for Safety Service metadata, and confirm Safety Service receives the pre-execution request before any adapter runs. | OpenClaw tool hook + request identity | integration | Bestanden | 2026-05-31 | OpenClaw safety hook tests passed; policy metadata redaction calls secret_redaction directly | AI Engineer
T11 | Schema, sub-agent output-constructor, and sub-agent status tests accept valid agent outputs, route output construction/model coercion and status vocabulary through shared modules, and reject missing status, malformed artifacts, invalid confidence, and unstructured errors. | SubAgentOutput + subagent_output_contracts.py + subagent_status.py | unit | Bestanden | 2026-05-31 | SubAgentOutput schema and shared constructor tests passed; final pytest 404 passed, 1 skipped, 1 warning | AI Engineer
T12 | Orchestration, sub-agent output-constructor, mock-agent-contract, sub-agent status, review-status, and numeric-utility tests route one request through all mock agents, collect structured outputs through the shared constructor, and synthesize status/confidence through shared agent/artifact vocabulary, output/error/synthesis/telemetry contracts, status aggregation, and rounded-average helpers. | Mock sub-agents + subagent_output_contracts.py + shared helpers + mock_agent_contracts.py | unit | Bestanden | 2026-05-31 | Mock sub-agent contract tests passed; output construction centralized in subagent_output_contracts.py; final pytest 404 passed, 1 skipped, 1 warning | AI Engineer
T13 | Cache, interface-type, operation, reason-message, and time-utility tests verify only read responses with OPA approval and non-expired UTC-created/cache-normalized entries are replayed through shared request-kind/operation constants, shared reason text, and direct shared UTC helpers. | Response cache + interface types + operations + reason messages + direct time utilities | unit | Bestanden | 2026-05-31 | Cache replay boundary tests passed; final pytest 313 passed, 1 skipped, 1 warning | Backend Engineer
T14 | Freshness, source-registry-contract, optional source-registry lookup, and time-utility tests increment source_data_registry.change_seq, verify UTC source timestamps, prove stale cached responses are blocked, and guard shared optional lookup behavior. | Source freshness + source_registry_contracts.py + find_source | unit | Bestanden | 2026-05-31 | Source freshness tests passed; optional source lookup centralized in find_source | Backend Engineer
T15 | Audit, observability, secret-redaction, and payload-field tests verify request, policy, reuse, execution-envelope, tool-call, and artifact events plus telemetry-safe mapping redaction. | Audit log + payload fields | unit | Bestanden | 2026-05-31 | Audit tests passed; redacted audit mapping helper shared with observability | Backend Engineer
T16 | Retrieval, knowledge-contract, sub-agent output-constructor, text-utility, contextual-snippet, and numeric-utility tests ingest sample source data, tokenize/embed it through shared helpers, query Qdrant with shared vector similarity, return source-cited results through centralized Knowledge Agent output/snippet contracts, and exclude unapproved sources. | Knowledge Agent + knowledge_contracts.py + subagent_output_contracts.py + text_utils.py | unit | Bestanden | 2026-05-31 | Knowledge Agent retrieval tests passed; output construction centralized in subagent_output_contracts.py; contextual snippets centralized in text_utils.py | AI Engineer
T17 | Shared model-coercion, direct operation, execution-gate, execution-gate-message, ComfyUI-contract, and time-utility tests plus adapter tests prove image generation is gated, uses centralized gate failure and required-envelope messages plus direct shared UTC expiry checks, and follows centralized generated-image URI conventions. | ComfyUI adapter + model coercion + execution gate + execution_gate_messages.py | integration | Bestanden | 2026-05-31 | T17 tests passed; gated adapter operation constants are called directly; final pytest 404 passed, 1 skipped, 1 warning | AI Engineer
T18 | Artifact, review-status, direct model-coercion, direct canonical-hash, payload-field, response-field, ComfyUI-contract, and time-utility tests verify image provenance and storage URI construction. | Image provenance + response fields + model coercion + canonical hashing + direct time utilities + comfyui_contracts.py | unit | Bestanden | 2026-05-31 | Image provenance tests passed; input coercion calls model_coercion.coerce_model directly | AI Engineer
T19 | Critic-rubric, review-status, text-utility, numeric-utility, direct numeric-clamp, and direct model-coercion tests score images with shared rubric vocabulary and direct shared scoring helpers. | Critic rubric vocabulary + direct numeric clamps + model coercion | unit | Bestanden | 2026-05-31 | Critic/Curator tests passed; score clamping calls numeric_utils.rounded_clamp directly | Domain Expert
T20 | Slack adapter, Slack-contract, connection-settings, request-identity, payload-field, and secret-redaction tests use a mocked Slack API to confirm inbound request normalization, nested event object validation, centralized Slack source labels, adapter validation messages, and runtime bot-token resolution, stable request IDs, direct shared helper usage at the adapter boundary, outbound response formatting, and token redaction. | Slack adapter + connection settings runtime secrets + request identity + payload fields + secret redaction + slack_contracts.py | integration | Bestanden | 2026-05-31 | Slack boundary helper tests passed; final pytest 300 passed, 1 skipped, 1 warning | Full-Stack Dev
T21 | Ingestion, source-ingestion-contract, canonical-hash, URL utility, and source-registry lookup tests import approved sample sources, store snapshots, record source registry rows, call shared approved-domain/rejection contracts, hash/version, URL-domain, and optional registry lookup helpers directly, create stable source version tags, and reject disallowed or non-http source domains. | Source ingestion + source_ingestion_contracts.py + canonical version tags + URL validation + find_source | unit | Bestanden | 2026-05-31 | Source ingestion contract tests passed; approved domains and rejection text centralized in source_ingestion_contracts.py; final pytest 404 passed, 1 skipped, 1 warning | Full-Stack Dev
T22 | Shared direct operation, execution-gate, execution-gate-message, canonical ID, response-field, publishing-status, side-effect audit, and publishing tests prove external publishing remains blocked until human approval is attached and audit operation/status plus required-envelope errors are read through shared operation/response/status/message boundaries. | Publishing approval + response fields + operations + execution gate; publishing statuses use publishing_status.py + execution_gate_messages.py | unit | Bestanden | 2026-05-31 | T22 tests passed; gated adapter operation constants are called directly; final pytest 404 passed, 1 skipped, 1 warning | Full-Stack Dev
T23 | GitHub adapter, GitHub-contract, connection-settings, execution-gate-message, direct operation registry, URL utility, HTTP-method, and adapter-result tests use a mocked GitHub API, resolve git_ai-artist_codex_token through the shared runtime secret resolver, call shared operation and URL path validation directly, reject unsafe API paths and non-write methods before token reads, centralize required-envelope and GitHub adapter validation errors, and confirm the token is read only by the adapter, not agents. | GitHub adapter + connection settings runtime secrets + operations + URL validation + HTTP methods + execution_gate_messages.py + github_contracts.py | integration | Bestanden | 2026-05-31 | T23 tests passed; gated adapter operation constants are called directly; final pytest 404 passed, 1 skipped, 1 warning | Full-Stack Dev
T24 | CI test suite runs canonicalizer, health-contract, request-metadata, classification-contract, sub-agent output-constructor, direct runtime interface-type imports, registry-driven connection settings/runtime env/runtime secret/env-access guard/endpoint URL composition/env-example rendering and shell-command construction/process execution/delimited output parsing and readiness backup path contracts and repo-root/workspace/repo artifact path/source-read/backend-module-discovery/raw-open-source-inspection contracts, canonical hashing/version tags/HMAC signatures/security-review/test-serialization/text-hash/image-provenance-hash contracts, source-ingestion approved-domain/rejection contracts, direct source-ingestion hash/version and URL-domain boundaries, source-registry missing-row message contracts and optional lookup, execution-gate failure and required-envelope message contracts, direct request identity/trace IDs, runtime IDs, mapping utilities, cache request-kind/operation constants, cache/policy/execution reason messages, sub-agent statuses, mock-agent contracts including orchestration output/error/synthesis/telemetry text, Knowledge Agent contracts and contextual snippets, ComfyUI contracts including response validation messages, review statuses, critic rubric vocabulary, Slack and GitHub contract and boundary helper usage, shared secret detection/redaction and file-scanning boundaries, direct gated-adapter operation constants, publishing operation/status boundaries, observability constants and redacted audit mappings, direct text utilities, Markdown heading utilities, direct numeric utility use at rubric boundaries, time utilities with direct-wrapper and test current-time guards, payload fields/nested objects, response fields including first-choice message parsing, URL utilities with direct connector-boundary usage, HTTP method normalization, operation registry, direct model coercion at adapter/domain boundaries, classifier, OPA, cache, freshness, and audit unit tests with --cov-fail-under=90 over the safety service modules. | Safety Service + classification_contracts.py + source_ingestion_contracts.py + connection endpoint/env-example rendering + shell_commands.py + readiness_paths.py + repo_paths.py + shared helpers | unit | Bestanden | 2026-05-31 | Unit CI coverage gate passed; readiness backup and repo-root/workspace/repo artifact path/source-read/backend-module-discovery/raw-open-source-inspection contracts included in coverage; final pytest 404 passed, 1 skipped, 1 warning | QA Engineer
T25 | End-to-end test sends request through OpenClaw hook, Safety Service, mock agents, validation, and final synthesis. | Integration CI | integration | Bestanden | 2026-05-31 | OpenClaw-to-safety integration tests passed | QA Engineer
T26 | Telemetry, request-metadata, audit-redaction, and observability-constant tests verify trace ids, metrics, structured logs, stage constants, log-level constants, shared workspace/agent metadata mappings, and shared redacted mapping helpers are used for request, policy, cache, orchestration, and tool stages. | Observability + request_metadata.py + audit redaction | unit | Bestanden | 2026-05-31 | Observability tests passed; request metadata mapping centralized for request fingerprints and observability fields | DevOps Lead
T27 | Shared detection/redaction/file-scanning tests and security checklist tests scan logs, prompts, memory, audit payloads, artifacts, and canonical JSON serialization paths for secret patterns, assignment-style leaks, and policy bypasses. | Security review | security | Bestanden | 2026-05-31 | Security review tests passed; reviewable text-file discovery centralized in file_scanning.iter_review_text_files | Projektleiter
T28 | Readiness, connection-settings, shell-command, readiness-path, repo-path, health-contract, and Markdown utility tests confirm runbooks, backups, restore check, env validation, centralized .env.example rendering, centralized service URL composition, shell command construction/process execution/delimited output parsing, backup directories, container dump path, MinIO source alias, Compose/env/runbook/OPA/PostgreSQL schema paths, centralized health-check expected signals, retention policy, incident contacts, and shared Markdown heading parsing exist. | Production readiness + shell_commands.py + readiness_paths.py + repo_paths.py + connection env/example and endpoint URLs + health_contracts.py + markdown_utils.py | unit | Bestanden | 2026-05-31 | Production readiness and repo path tests passed; repo artifact paths, repo-root lookup, workspace file lookups, backend module discovery, and backend module source reads flow through repo_paths.py; final pytest 404 passed, 1 skipped, 1 warning | DevOps Lead

## Interfaces
INTERFACE STANDARD - AI-ARTIST OPENCLAW + LLM API
From | To | Payload | Interface | Rule | Validation | Status | Finished
OpenClaw Gateway | FastAPI Safety Service | RequestEnvelope | POST /v1/requests/canonicalize; /classify; /policy/evaluate; /reuse/check; /execution/envelope; /audit/events | OpenClaw sends task context only; no secrets. | Safety service endpoint, request identity, and integration tests passed | Bestanden | 2026-05-31
FastAPI Safety Service | OPA | PolicyInput | POST /v1/data/ai_artist/allow | OPA is authority for reuse and privileged execution. | OPA allow/deny tests passed | Bestanden | 2026-05-31
OpenClaw Runtime | Sub-Agents | SubAgentTask -> SubAgentOutput | delegate_task | Sub-agents return structured outputs only. | SubAgentOutput schema tests passed | Bestanden | 2026-05-31
OpenClaw Tool Hook | Output Tool Agent | ExecutionEnvelope | pre-execution hook | External writes require signed envelope. | Execution gate, direct UTC time utility, request identity trace, and OpenClaw hook tests passed | Bestanden | 2026-05-31
Image-Gen Agent | ComfyUI Adapter | ImageGenerationRequest | adapter.generate_image | Image generation is blocked without envelope. | ComfyUI adapter execution-gate and response-field tests passed | Bestanden | 2026-05-31
ComfyUI Adapter | MinIO/PostgreSQL | ImageArtifactMetadata | artifact save + metadata insert | Prompt/workflow hashes and review status required. | Image provenance, response-field, payload field, canonical hash, and direct UTC time utility tests passed | Bestanden | 2026-05-31
Knowledge Agent | Qdrant/PostgreSQL/MinIO | RetrievalRequest/SourceCitation | search + source lookup | Every cited answer includes source refs. | Source ingestion, retrieval, text utility, numeric utility, and URL utility tests passed | Bestanden | 2026-05-31
GitHub Adapter | GitHub API | GitHubActionRequest | mocked API in tests | Token read only by adapter process. | GitHub adapter, connection-settings runtime secret, URL utility, and adapter-result tests passed | Bestanden | 2026-05-31
Slack Adapter | Slack API | ChannelMessage | mocked API in tests | Dev channel first; publishing later. | Slack adapter, request identity, and payload-field object tests passed | Bestanden | 2026-05-31
Audit Agent | PostgreSQL | AuditEvent | insert audit_event | Correlation id required for all sensitive paths. | Audit and payload-field scope extraction tests passed | Bestanden | 2026-05-31

## Project Status
PROJECT STATUS - AI-ARTIST OPENCLAW + LLM API
Status Date | 2026-05-31 |  | Overall Status | All 28 implementation tasks complete and locally validated
Control Plane | OpenClaw |  | LLM Backend | Provider-neutral LLM API
Safety Layer | FastAPI Safety Service + OPA + PostgreSQL |  | Image Layer | ComfyUI behind execution policy gate
Tasks Total | 28 |  | Completed | 28
In Progress | 0 |  | Open | 0
Validation Tests | 28 |  | Validation Passed | 28
Validation Pending | 0 |  | Interface Contracts | 28
Next Task | Operate from production runbook and keep validation gates green |  | Next Gate | maintenance + shared-helper regression checks
Deprecated Term Scan | Clean |  | Formula Error Scan | Clean
Implementation Readiness | final pytest 404 passed, 1 skipped, 1 warning; ruff clean; classification response contract centralized in classification_contracts.py; RequestMetadata mapping centralized in request_metadata.py; SubAgentOutput construction centralized in subagent_output_contracts.py; Safety Service health contract centralized in health_contracts.py; contextual snippets centralized in text_utils.py; gated adapters call shared operation constants directly; publishing audit operation values use OPERATION_PUBLISH directly; optional source registry lookup centralized; source ingestion contracts centralized; connection endpoint URLs centralized; env-example rendering centralized; shell command construction/process execution/delimited output parsing centralized; readiness paths centralized; repo artifact paths centralized; standard LLM API key is deepseek-open-art; DEEPSEEK_API_KEY is compatibility-only; runbook heading parsing, file scanning, secret detection, numeric clamps, execution gate messages, source registry messages, model coercion, response fields, payload fields, operation registry, URL validation, time/numeric/direct text utilities, canonical hashing/HMAC signatures, request identity, side-effect audit, adapter results, secret redaction, and execution gates centralized |  | Do Not Start Yet | Production external writes, real social APIs, or real ComfyUI execution without execution-envelope approval
Source Of Truth | docs/project_status_latest_v1.md |  | Tracker | Dashboard + Detailplan + Validation + Interfaces
Completed | Task | Status | Finished | Evidence
T01 | Stack decision: OpenClaw + provider-neutral LLM API | Bestanden | 2026-05-30 | Docs/tracker validation passed
T02 | Project documentation and tracker alignment | Bestanden | 2026-05-30 | Docs/tracker validation passed
T03 | Repository scaffold | Bestanden | 2026-05-31 | pytest/ruff/tree checks passed
T04 | Docker Compose services | Bestanden | 2026-05-31 | docker compose ps reports all services healthy
T05 | FastAPI Safety Service endpoints | Bestanden | 2026-05-31 | Safety Service endpoint and classification-contract tests passed; final pytest 404 passed, 1 skipped, 1 warning
T06 | OPA default-deny policies | Bestanden | 2026-05-31 | OPA default-deny policy tests passed
T07 | PostgreSQL migrations | Bestanden | 2026-05-31 | PostgreSQL migration rollback test passed
T08 | OpenClaw AI-Artist workspace | Bestanden | 2026-05-31 | OpenClaw workspace tests passed
T09 | Provider-neutral LLM API configuration | Bestanden | 2026-05-31 | Provider-neutral LLM API mocked smoke test passed; response id/model/content read through shared response fields and first-choice message parser; live test requires deepseek-open-art
T10 | OpenClaw safety-service tool hook | Bestanden | 2026-05-31 | OpenClaw safety hook tests passed; policy metadata redaction calls secret_redaction.redact_secret_value directly
T11 | SubAgentOutput schema | Bestanden | 2026-05-31 | SubAgentOutput schema and shared constructor tests passed; final pytest 404 passed, 1 skipped, 1 warning
T12 | Mock sub-agents | Bestanden | 2026-05-31 | Mock sub-agent contract tests passed; output construction centralized in subagent_output_contracts.py; final pytest 404 passed, 1 skipped, 1 warning
T13 | Approved read-only response cache | Bestanden | 2026-05-31 | Approved response cache tests passed; cache replay uses shared request-kind and operation constants plus shared reason text; final pytest 313 passed, 1 skipped, 1 warning
T14 | Source freshness check | Bestanden | 2026-05-31 | Source freshness tests passed; optional source lookup centralized in find_source
T15 | Audit event log | Bestanden | 2026-05-31 | Audit event log tests passed; redacted audit mapping helper shared with observability fields and tags
T16 | Knowledge Agent retrieval | Bestanden | 2026-05-31 | Knowledge Agent retrieval tests passed; output construction centralized in subagent_output_contracts.py; contextual snippets centralized in text_utils.py
T17 | ComfyUI adapter behind execution gate | Bestanden | 2026-05-31 | ComfyUI adapter and execution gate message tests passed; failure messages centralized in execution_gate_messages.py
T18 | Image provenance | Bestanden | 2026-05-31 | Image provenance tests passed; input coercion calls model_coercion.coerce_model directly
T19 | Critic/Curator rubrics | Bestanden | 2026-05-31 | Critic/Curator tests passed; score clamping calls numeric_utils.rounded_clamp directly
T20 | Slack development channel | Bestanden | 2026-05-31 | Slack adapter tests passed; payload parsing, request identity, and token redaction call shared helpers directly; final pytest 300 passed, 1 skipped, 1 warning
T21 | Source ingestion | Bestanden | 2026-05-31 | Source ingestion contract tests passed; approved domains and rejection text centralized in source_ingestion_contracts.py; final pytest 404 passed, 1 skipped, 1 warning
T22 | Publishing Agent with human approval | Bestanden | 2026-05-31 | Publishing tests passed; audit operation uses OPERATION_PUBLISH directly; final pytest 344 passed, 1 skipped, 1 warning
T23 | GitHub adapter | Bestanden | 2026-05-31 | GitHub adapter tests passed; token lookup uses connection_settings.require_runtime_secret; HTTP write-method validation centralized in http_methods.py; API path validation calls url_utils.safe_relative_api_path directly; final pytest 404 passed, 1 skipped, 1 warning
T24 | Unit tests for safety service and policies | Bestanden | 2026-05-31 | Unit CI coverage gate passed; readiness backup and repo-root/workspace/repo artifact path/source-read/backend-module-discovery/raw-open-source-inspection contracts included in coverage; final pytest 404 passed, 1 skipped, 1 warning
T25 | OpenClaw-to-safety integration tests | Bestanden | 2026-05-31 | OpenClaw-to-safety integration tests passed
T26 | Observability | Bestanden | 2026-05-31 | Observability tests passed; request metadata mapping centralized for request fingerprints and observability fields
T27 | Security review | Bestanden | 2026-05-31 | Security review tests passed; reviewable text-file discovery centralized in file_scanning.iter_review_text_files
T28 | Production hardening and runbooks | Bestanden | 2026-05-31 | Production readiness and repo path tests passed; repo artifact paths, repo-root lookup, workspace file lookups, backend module discovery, and backend module source reads flow through repo_paths.py; final pytest 404 passed, 1 skipped, 1 warning
Execution-envelope messages | centralized in backend/execution_gate_messages.py |  | Alignment | shared across ComfyUI, Publishing, GitHub, and execution gate validation errors
Slack adapter contracts | centralized in backend/slack_contracts.py |  | Alignment | shared across source labels, inbound event validation messages, and outbound response validation messages
GitHub adapter contracts | centralized in backend/github_contracts.py |  | Alignment | shared across action labels, target labels, API validation messages, and token-purpose text
Source ingestion contracts | Centralized approved-domain defaults and rejection messages in backend/source_ingestion_contracts.py | Bestanden | 2026-05-31 | Shared across source ingestion URL validation and domain allowlist rejection paths
Connection endpoint URLs | Centralized service endpoint composition in backend/connection_settings.py | Bestanden | 2026-05-31 | Shared across readiness health, backup, and restore command definitions
Connection env example rendering | Centralized .env.example rendering in backend/connection_settings.py | Bestanden | 2026-05-31 | Checked-in .env.example matches shared connection registry rendering exactly
Shell command construction | Centralized Docker Compose, curl, and MinIO command construction in backend/shell_commands.py | Bestanden | 2026-05-31 | Readiness health, backup, and restore command definitions use shared shell command helpers
Readiness backup paths | Centralized backup directories, Postgres dump path, and MinIO source alias in backend/readiness_paths.py | Bestanden | 2026-05-31 | Readiness backup and restore command definitions use shared path contracts
Repository artifact paths | Centralized Compose, env, runbook, OPA policy, and PostgreSQL schema paths in backend/repo_paths.py | Bestanden | 2026-05-31 | Security review, scaffold, OPA, and readiness validators use shared repo path contracts